## Instructions
Bug Tracker Template
Instructions: What is this chart? How do I work it?
Team behaviour relating to bugs, over time
How's your quality? Do you trust your QA and feedback loops to be identifying bugs? Do you welcome those bugs with open arms, and record them for fixing? If the answers are yes, then how are you dealing with known bugs? Are you committed to fixing them first? Even at thje cost of percieved feature "progress"?
This chart will help you monitor the count of bugs recorded and fixed during your iterations, clearly showing trends in bug confirmations, bug fixes and known bugs recorded in your backlog. It'll help communicate the importance of an ongoing commitment to quality within the team and outside too."
How do I use this Template?
Simply, replace the sample data on the "Project Data" and "Sprint Data" sheets. There's sample data in there to show you what goes where. Just replace all that. Bug counts, Dates, everything in a WHITE cell.
Overwrite the content of the white cells, don't delete rows or the calcs in the grey cells!
By entering the Project and Sprint details, the chart will just happen. Use as many rows as you need to the "Input" sheet, but remember:
Don't mess with the Grey Cells or the "Calc" sheet, as they prepare the input for the chart that follows.
What does the chart show?
The chart itself is found on the "Bugs over time" sheet. The RED line shows the number of bugs ADDED to the backlog in each sprint. This line will continue upward forever, as long as bugs are being reported.
The BLUE line shows the number of bugs FIXED in each sprint. This line will continue upward, as long as you keep fixing bugs!
The story is in the difference. Theoretically, the blue line can never surpass the red one (you can't fix more bugs than have been reported), and if the gap between the red and blue lines keeps widening, it won't be long until you're quality issues get away from you.
That gap represents the number of outstanding bugs at any moment in the project timeline. It's also shown at the bottom of the chart in YELLOW. A rising yellow area means that the known bugs are mounting up faster than they are being fixed."
You are free copy this doc, and use it in any way you like. Knock yourself out. It'd be great if you could post a link back to the blog (somewhere) if you find the charts give you some help at work. You'll also find Google Docs versions of some of my charts at the website.
http://scrumage.com/
If you find any errors, or think of ways to improve these charts, don't keep it to yourself. Any feedback at all is great.
Adrian
adfit11@gmail.com
http://www.scrumage.com

## Project Data
First Sprint Start Date | 2012-07-02
First Sprint End Date | 2013-07-06
Sprint Cycle (# Days, start-to-start) | 7

## Sprint Data
Sprint | Begin Date | Finish Date | Bugs ADDED during sprint | Bugs FIXED during sprint | Bugs remaining
1 | 2012-07-02 | 2013-07-06 | 5 | 3 | 2
2 | 2012-07-09 | 2013-07-13 | 6 | 4 | 4
3 | 2012-07-16 | 2013-07-20 | 7 | 1 | 10
4 | 2012-07-23 | 2013-07-27 | 2 | 6 | 6
5 | 2012-07-30 | 2013-08-03 | 1 | 4 | 3
6 | 2012-08-06 | 2013-08-10 | 5 | 5 | 3
7 | 2012-08-13 | 2013-08-17 | 4 | 7 | 0
8 | 2012-08-20 | 2013-08-24 | 3 | 1 | 2
9 | 2012-08-27 | 2013-08-31 | 0 | 0 | 2
10 | 2012-09-03 | 2013-09-07 | 0 | 2 | 0
11 | 2012-09-10 | 2013-09-14 | 0 | 0 | 0
12 | 2012-09-17 | 2013-09-21 | 0 | 0 | 0
13 | 2012-09-24 | 2013-09-28 | 20 | 10 | 10
14 | 2012-10-01 | 2013-10-05 | 25 | 10 | 25
15 | 2012-10-08 | 2013-10-12 |  |  | 0
16 | 2012-10-15 | 2013-10-19 |  |  | 0
17 | 2012-10-22 | 2013-10-26 |  |  | 0
18 | 2012-10-29 | 2013-11-02 |  |  | 0
19 | 2012-11-05 | 2013-11-09 |  |  | 0
20 | 2012-11-12 | 2013-11-16 |  |  | 0
21 | 2012-11-19 | 2013-11-23 |  |  | 0
22 | 2012-11-26 | 2013-11-30 |  |  | 0
23 | 2012-12-03 | 2013-12-07 |  |  | 0
24 | 2012-12-10 | 2013-12-14 |  |  | 0
25 | 2012-12-17 | 2013-12-21 |  |  | 0
26 | 2012-12-24 | 2013-12-28 |  |  | 0
27 | 2012-12-31 | 2014-01-04 |  |  | 0
Formulas:
Begin Date = IF((([Sprint]+[Sprint])=0),,([Begin Date, row above]+'Project Data'!$C4))
Finish Date = IF((([Sprint]+[Sprint])=0),,([Finish Date, row above]+'Project Data'!$C4))

## Calc
|  | Date | Bugs Reported (All time) | Bugs Resolved (All time) | Bugs in Backlog (point in time)
5 | 3 | 2013-07-06 | 5 | 3 | 2
6 | 4 | 2013-07-13 | 11 | 7 | 4
7 | 1 | 2013-07-20 | 18 | 8 | 10
2 | 6 | 2013-07-27 | 20 | 14 | 6
1 | 4 | 2013-08-03 | 21 | 18 | 3
5 | 5 | 2013-08-10 | 26 | 23 | 3
4 | 7 | 2013-08-17 | 30 | 30 | 0
3 | 1 | 2013-08-24 | 33 | 31 | 2
0 | 0 | 2013-08-31 | 33 | 31 | 2
0 | 2 | 2013-09-07 | 33 | 33 | 0
0 | 0 | 2013-09-14 | 33 | 33 | 0
0 | 0 | 2013-09-21 | 33 | 33 | 0
20 | 10 | 2013-09-28 | 53 | 43 | 10
25 | 10 | 2013-10-05 | 78 | 53 | 25
0 | 0 | 2013-10-12 | 78 | 53 | 25
0 | 0 | 2013-10-19 | 78 | 53 | 25
0 | 0 | 2013-10-26 | 78 | 53 | 25
0 | 0 | 2013-11-02 | 78 | 53 | 25
0 | 0 | 2013-11-09 | 78 | 53 | 25
0 | 0 | 2013-11-16 | 78 | 53 | 25
0 | 0 | 2013-11-23 | 78 | 53 | 25
0 | 0 | 2013-11-30 | 78 | 53 | 25
0 | 0 | 2013-12-07 | 78 | 53 | 25
0 | 0 | 2013-12-14 | 78 | 53 | 25
0 | 0 | 2013-12-21 | 78 | 53 | 25
0 | 0 | 2013-12-28 | 78 | 53 | 25
0 | 0 | 2014-01-04 | 78 | 53 | 25