## Instructions
Project Forecast Template
Instructions: What is this chart? How do I work it?
These are my favourite charts of all time!
Most teams track velocity of course, for the purpose of future planning. This chart goes further.
Simplistically, deriving an estimated project completion date is a matter of dividing the story point size of the product backlog, by the team’s known velocity. 100 points in the backlog will probably be consumed in 5 iterations by a team whose velocity is 20. Not an exact science, but the idea pretty much underpins agile project planning.
The Forecast Lighthouse, will track velocity and known/estimated backlog, combining the two, to make a prediction about the project completion date.
The Time and Budget chart also makes a prediction, but in addition, tracks the budget % used in order to guide spending.
The real bonus from this chart is the visibility of scope creep, and the impact of that particular variable on the deadline."
How do I use this Template?
Simply replace the sample data on the "Project Data" and "Sprint Data" sheets. There's sample data in there to show you what goes where. Just replace all that. Names, Dates, everything that'e in a WHITE cell.
Overwrite the content of the white cells, don't delete rows or the calcs in the grey cells!
By entering the Project and Sprint details, the chart will just happen. Use as many rows as you need to the "Input" sheet, but remember:
Don't mess with the Grey Cells or the "Calc" sheet, as they prepare the input for the chart that follows.
Important: Your product backlog may not always be in pristine condition. There'll be times when you know (you just KNOW!) that the PBL is incomplete, or there are stories in there that are unestimated. For this reason, you'll see the "Assumed % of scope estimated" field on the Sprint Data sheet. If you feel like the number of story points in the backlog represents only half of the work you know you're gonna need to do, put 50% in there, next to the "Story Points in Product Backlog". The chart will compensate for that in its Backlog size, and adjust the projected date too.
Lighthouse Chart
The grey bars on the chart above are the team’s velocity. See it grow over the first few iterations, as the team finds its feet. The red area shows the known and estimated backlog, current at the beginning of each sprint. This is the known scope. See how it too grows over the first few iterations? It's an illustration of scope growth. As long as the scope continues to grow ahead of the team’s capacity to consume story points, the project will never be done!
Note: This pattern is normal in Agile projects. We need to expect and embrace this! By starting as soon as we know enough to do so, we create a loop for feedback, and an approach for discovery. All of that helps build out the backlog as we go! In a project scenario though, the known scope will at some point need to slow or stop growing, or we'll never be done.This chart just makes that visible, and helps you to keep an eye on the impact of an ever burgeoning backlog on your delivery date.
The angled lines descending from the known scope-points, fall upon an estimated completion date. The estimate is true to what is (was) known at any time in the project lifecycle. This calculation is made by averaging velocity over the previous 2 iterations (yesterday’s weather), and dividing the known scope by that burn rate.
Time and budget
Similar to a traditional "earned value" chart, focused on monitoring spend vs completion. The chart makes a guideline for projected completion and budget exhaustion, so you can learn early about the status of each. The "ideal line" simply shows the perfect spend/progress line. Needless to say, it's alway good to have the spend and progress lines above or around this. If the budget line is above the ideal, and the completed line below, there's trouble ahead!
You are free copy this doc, and use it in any way you like. Knock yourself out. It'd be great if you could post a link back to the blog (somewhere) if you find the charts give you some help at work!
http://scrumage.com/
If you find any errors, or think of ways to improve these charts, don't keep it to yourself. Any feedback at all is great.
Adrian
adfit11@gmail.com
http://scrumage.com/

## Project Data
Number of Sprints (1-26) | 20
First Sprint Start Date | 2012-07-02
First Sprint End Date | 2012-07-13
Sprint Cycle (# Days, start-to-start) | 14

## Sprint Data
Sprint | Begin Date | Finish Date | At START of Sprint | At START of Sprint | At END of Sprint | At END of Sprint
|  |  | Assumed % of scope estimated | Story Points in Product Backlog | Story Points Done in Sprint | % of Budget Spent
1 | 2012-07-02 | 2012-07-13 | 40% | 37 | 18 | 10%
2 | 2012-07-16 | 2012-07-27 | 75% | 91 | 28 | 12%
3 | 2012-07-30 | 2012-08-10 | 75% | 113 | 37 | 25%
4 | 2012-08-13 | 2012-08-24 | 80% | 143 | 46 | 30%
5 | 2012-08-27 | 2012-09-07 | 90% | 159 | 56 | 45%
6 | 2012-09-10 | 2012-09-21 | 80% | 158 | 56 | 55%
7 | 2012-09-24 | 2012-10-05 | 80% | 105 | 51 | 65%
8 | 2012-10-08 | 2012-10-19
9 | 2012-10-22 | 2012-11-02
10 | 2012-11-05 | 2012-11-16
11 | 2012-11-19 | 2012-11-30
12 | 2012-12-03 | 2012-12-14
13 | 2012-12-17 | 2012-12-28
14 | 2012-12-31 | 2013-01-11
15 | 2013-01-14 | 2013-01-25
16 | 2013-01-28 | 2013-02-08
17 | 2013-02-11 | 2013-02-22
18 | 2013-02-25 | 2013-03-08
19 | 2013-03-11 | 2013-03-22
20 | 2013-03-25 | 2013-04-05
21 | 2013-04-08 | 2013-04-19
22 | 2013-04-22 | 2013-05-03
23 | 2013-05-06 | 2013-05-17
24 | 2013-05-20 | 2013-05-31
25 | 2013-06-03 | 2013-06-14
26 | 2013-06-17 | 2013-06-28
27 | 2013-07-01 | 2013-07-12
Formulas:
Begin Date = IF((([Sprint]+[Sprint])=0),,([Begin Date, row above]+'Project Data'!$C5))
Finish Date = IF((([Sprint]+[Sprint])=0),,([Finish Date, row above]+'Project Data'!$C5))

## Calc (NO Edit)
Date | Acc. Pts | # | Stories | Burn | % Est | Date | Pts | BL | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Project BL | Proj. Start | Assumed Complete | Budget Spent | Ideal
2012-07-13 | 18 | 1 | 18 |  | 0.4 | 2012-07-02 | 18 | 92.5 | [25 empty] | 110.5 | 2012-07-13 | 16.29% | 10% | #N/A | 2013-04-08
2012-07-27 | 46 | 2 | 28 | 18 | 0.75 | 2012-07-16 | 28 | 121.3333 | 121.3333 | [24 empty] | 167.3333 | 2012-07-27 | 27.49% | 12% | #N/A | 2013-04-08
2012-08-10 | 83 | 3 | 37 | 23 | 0.75 | 2012-07-30 | 37 | 150.6667 | 103.3333 | 150.6667 | [23 empty] | 233.6667 | 2012-08-10 | 35.52% | 25% | #N/A | 2013-04-08
2012-08-24 | 129 | 4 | 46 | 32.5 | 0.8 | 2012-08-13 | 46 | 178.75 | 85.3333 | 127.6667 | 178.75 | [22 empty] | 307.75 | 2012-08-24 | 41.92% | 30% | #N/A | 2013-04-08
2012-09-07 | 185 | 5 | 56 | 41.5 | 0.9 | 2012-08-27 | 56 | 176.6667 | 67.3333 | 104.6667 | 146.25 | 176.6667 | [21 empty] | 361.6667 | 2012-09-07 | 51.15% | 45% | #N/A | 2013-04-08
2012-09-21 | 241 | 6 | 56 | 51 | 0.8 | 2012-09-10 | 56 | 197.5 | 49.3333 | 81.6667 | 113.75 | 135.1667 | 197.5 | [20 empty] | 438.5 | 2012-09-21 | 54.96% | 55% | #N/A | 2013-04-08
2012-10-05 | 292 | 7 | 51 | 56 | 0.8 | 2012-09-24 | 51 | 131.25 | 31.3333 | 58.6667 | 81.25 | 93.6667 | 146.5 | 131.25 | [19 empty] | 423.25 | 2012-10-05 | 68.99% | 65% | #N/A | 2013-04-08
2012-10-19 | 0 | 8 | 0 | 53.5 | 0 | 2012-10-08 | 0 | #DIV/0! | 13.3333 | 35.6667 | 48.75 | 52.1667 | 95.5 | 75.25 | #DIV/0! | [19 empty] | 2012-10-19 | #N/A | #N/A | #N/A | 2013-04-08
2012-11-02 | 0 | 9 | 0 | 25.5 | 0 | 2012-10-22 | 0 | #DIV/0! | -4.6667 | 12.6667 | 16.25 | 10.6667 | 44.5 | 19.25 | #DIV/0! | #DIV/0! | [18 empty] | 2012-11-02 | #N/A | #N/A | #N/A | 2013-04-08
2012-11-16 | 0 | 10 | 0 | 0 | 0 | 2012-11-05 | 0 | #DIV/0! | 0 | -10.3333 | -16.25 | -30.8333 | -6.5 | -36.75 | #DIV/0! | #DIV/0! | #DIV/0! | [17 empty] | 2012-11-16 | #N/A | #N/A | #N/A | 2013-04-08
2012-11-30 | 0 | 11 | 0 | 0 | 0 | 2012-11-19 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 2012-11-30 | #N/A | #N/A | #N/A | 2013-04-08
2012-12-14 | 0 | 12 | 0 | 0 | 0 | 2012-12-03 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [15 empty] | 2012-12-14 | #N/A | #N/A | #N/A | 2013-04-08
2012-12-28 | 0 | 13 | 0 | 0 | 0 | 2012-12-17 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [14 empty] | 2012-12-28 | #N/A | #N/A | #N/A | 2013-04-08
2013-01-11 | 0 | 14 | 0 | 0 | 0 | 2012-12-31 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [13 empty] | 2013-01-11 | #N/A | #N/A | #N/A | 2013-04-08
2013-01-25 | 0 | 15 | 0 | 0 | 0 | 2013-01-14 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [12 empty] | 2013-01-25 | #N/A | #N/A | #N/A | 2013-04-08
2013-02-08 | 0 | 16 | 0 | 0 | 0 | 2013-01-28 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [11 empty] | 2013-02-08 | #N/A | #N/A | #N/A | 2013-04-08
2013-02-22 | 0 | 17 | 0 | 0 | 0 | 2013-02-11 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [10 empty] | 2013-02-22 | #N/A | #N/A | #N/A | 2013-04-08
2013-03-08 | 0 | 18 | 0 | 0 | 0 | 2013-02-25 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [9 empty] | 2013-03-08 | #N/A | #N/A | #N/A | 2013-04-08
2013-03-22 | 0 | 19 | 0 | 0 | 0 | 2013-03-11 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [8 empty] | 2013-03-22 | #N/A | #N/A | #N/A | 2013-04-08
2013-04-05 | 0 | 20 | 0 | 0 | 0 | 2013-03-25 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [7 empty] | 2013-04-05 | #N/A | #N/A | 100% | 2013-04-08
2013-04-19 | 0 | 21 | 0 | 0 | 0 | 2013-04-08 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | 2013-04-19 | #N/A | #N/A | 100% | 2013-04-08
2013-05-03 | 0 | 22 | 0 | 0 | 0 | 2013-04-22 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [5 empty] | 2013-05-03 | #N/A | #N/A | 100% | 2013-04-08
2013-05-17 | 0 | 23 | 0 | 0 | 0 | 2013-05-06 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  |  | 2013-05-17 | #N/A | #N/A | 100% | 2013-04-08
2013-05-31 | 0 | 24 | 0 | 0 | 0 | 2013-05-20 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 2013-05-31 | #N/A | #N/A | 100% | 2013-04-08
2013-06-14 | 0 | 25 | 0 | 0 | 0 | 2013-06-03 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 2013-06-14 | #N/A | #N/A | 100% | 2013-04-08
2013-06-28 | 0 | 26 | 0 | 0 | 0 | 2013-06-17 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 2013-06-28 | #N/A | #N/A | 100% | 2013-04-08