## Instructions
Sprint Burn Down Templates
Instructions: What are these charts? How do I work them?
Classic Agile Iteration Charts
The most common and popularly used agile charts are those that track activity during a sprint. Probably the two best known are the “burn up” and “burn down” charts. Although these titles are often transposed, here we'll use the example of a burned DOWN for hours, and burn UP for story points. The additional Cumulative flow chart can help you to identify bottlenecks in your workflow.
How do I use this Template?
Make a copy of the "Sprint 21" sheet, for each iteration you run. There's sample data in there to show you what goes where. Have a look at whet's there, but you'll want to start (on day 1 of all your sprints) by deleting all the data in the WHITE cells, so you can chart your own iteration. Start with the sprint data at the top, and then make the appropriate updates daily in the grids below. Update everything that's in a WHITE cell, and the charts below will just happen. The charts themselves are found below the input grids, so that you have independent charts for each sprint and a history (sprint signature tracking).
Overwrite the content of the white cells, don't delete rows or the calcs in the grey or coloured cells!
By entering data in the input grids, the charts will just happen, but remember:
Don't mess with the Grey or Coloured Cells, as they prepare the input for the charts that follow.
Important: The "Stories in play" grid tracks the number of stories (not story points) in each phase of development. The sample phases there are the ones that we use. You should replace those with your own, STARTING WITH YOUR FIRST PHASE AT THE BOTTOM. Follow the numbers. If you have less phases, don't delete rows, just replace the status labels, and leave blank rows above.
What do the charts show?
Burn Down
Tracks: Estimated number of hours (effort) remaining to complete the sprint goal.
The hours burn down chart is created every day, immediately after the stand-up meeting. The Scrum Master adds up all of the estimated hours remaining on all incomplete user stories. By plotting these on a chart that also shows the total number of hours available to the team in the remaining days of the Sprint, we can see whether things are on track, ahead or behind schedule. Conversations can then be had about whether or not the sprint goal is realistic.
Burn Up
Tracks: Story points completed daily, throughout a sprint.
Some teams make a burn down of story points remaining to be completed, not hours. For differentiation, we’re going to call that type of chart a burn “UP”. It’s very similar to the burn down, but rather than tracking work still to be done, it tracks work that has been completed. In the example provided, we can see the accumulation of user story points throughout the course of a sprint.
Cumulative Flow
Tracks: Efficiency through stages in the delivery process
Your workflow is only as efficient as its slowest required action. The cumulative flow diagram highlights workflow bottlenecks, by charting the progress of stories through each stage of the sprint. The coloured bands each represent one stage in the development workflow. In a true “pull” system, a widening of any of these coloured bands over time will indicate a bottleneck in the phase that follows it. It could in practice though (when used in Scrum), indicate a lag in the phase itself. In the provided example, we might look at the Testing phase, as the chart shows that user stories are tending to build up there in this Sprint.
You are free copy this doc, and use it in any way you like. Knock yourself out. It'd be great if you could post a link back to the blog (somewhere) if you find the charts give you some help at work!
http://scrumage.com/
If you find any errors, or think of ways to improve these charts, don't keep it to yourself. Any feedback at all is great.
Adrian
adfit11@gmail.com
http://scrumage.com/

## Sprint 21
Sprint Data
Developer Allocation | 8 | < Total Allocated Dev Resources
Tester Allocation | 2 | < Total Allocated Test Resources
Days | 10 | < Total number of days in Sprint (accounting for public holidays etc)
Points Target | 47 | < Story Points accepted by team(s) in this Sprint
Number of Stories | 18 | < Number of user stories accepted by team(s)
Burn Down
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Hrs | 449 | 432 | 444 | 370 | 300 | 244 | 180
Available Hrs (8hr days) | 720 | 648 | 576 | 504 | 432 | 360 | 288 | 216 | 144 | 72
Burn Up
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Pts. Done | 0 | 0 | 0 | 8 | 8 | 16 | 16
Pts. Predicted | 2.2857 | 4.5714 | 6.8571 | 9.1429 | 11.4286 | 13.7143 | 16 | 18.2857 | 20.5714 | 22.8571
Pts. Req. | 4.7 | 9.4 | 14.1 | 18.8 | 23.5 | 28.2 | 32.9 | 37.6 | 42.3 | 47
Stories in play
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
8. Done | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 6
7. Await Merge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6. Await Acc. | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
5. Testing | 0 | 0 | 3 | 3 | 4 | 5 | 5 | 0
4. Code Review | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2
3. Design Review | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0
2. In Progress | 5 | 5 | 3 | 4 | 3 | 5 | 5 | 5
1. To Do | 13 | 11 | 11 | 10 | 9 | 5 | 4 | 4
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18 | -18